## Slide 1
Synoptek Transition Plan
Pratyush Rai
July, 2025

## Slide 2: Executive Summary
Service Overview: Synoptek currently provides GGG with three core services — Security, Corporate IT, and DevOps.
Performance Concerns: Synoptek has consistently underperformed across all service areas. These shortcomings have negatively impacted productivity, employee morale, impeded speed to delivery, and driven up operational costs.
Transition Readiness: GGG is well-positioned to insource Security and DevOps services with minimal risk and at cost-neutral levels. Transitioning Corporate IT services internally is also feasible at cost-neutral levels, but will require deliberate planning around resourcing and execution.
Path Forward — Two Options:
  Option A: Transition all three services internally. This approach maintains a cost-neutral annual run rate but incurs a one-time transition cost and will require incremental hiring by early November for Corporate IT.
  Option B: Transition Security and DevOps internally; renew Synoptek’s contract for Corporate IT services for one additional year.

## Slide 3: The Problem with Synoptek: Slow Responses at a Premium Price
Synoptek’s response times lag behind industry expectations
Synoptek’s value proposition doesn’t match its cost
Chart: 
 | 26 | 34 | 42.4 | 138.5 | 113.4 | 112.4
 | 5 | 10 | 4 | 5 | 2 | 5
New Hire Onboarding
Equipment Order
Software + Application
Days
Data Storage Issues
User Identity Access Issues
Security Issues
Synoptek Median time
Desired time
Median time to resolve issues by Synoptek
(Jan – Jun 2025)
Synoptek Hourly Rates vs Other Firms (based on RPAG Cloud migration)
Chart: 
 | 100 | 100 | 250 | 250
 | 55 | 55 | 100 | 200
Security Engineer
Platform Engineer
DevOps Solution Architect
DBA
Synoptek
Other Firms

## Slide 4: Synoptek Provides Three Categories of Service
Primary Category
Sub-category
Security
Antivirus/antimalware agents
Threat detection functionaltiy
End State
CrowdStrike
CrowdStrike
24x7 staffed Security Operations Center (SOC) team
CrowdStrike + Internal resources
IT Services Corporate IT
Move Hardware Procurement Reseller to new reseller
New Reseller
Service desk operations transitioned to internal staffing model
Internal Management
DevOps
Azure subscriptions and billing under GGG
Self managed
Infrastructure management transitioned to staff
Self managed
Vulnerability scanning functionality
Log collection functionality
Security training functionality
Email security functionality
In 2025 Budget
CrowdStrike
CrowdStrike
KnowBe4
KnowBe4
Yes
Yes
Yes
Yes
Yes
Yes
Yes
N/A
No
Decommission Synoptek-specific tools & services
Internal Management
No
Migrate Microsoft account from Synoptek to GGG
Self managed
N/A
Monitoring transitoned to Azure-native tools & Atlassian ITSM
Self managed
N/A
Partial
Partial

## Slide 5: Synoptek Professional Services charges in 2025 will be ~$1.0M
Chart: 
 | 88790.5 | 53285.1667 | 77703.6667 | 88698 | 26233.3333 | 4469.5
Professional Services
Licenses
Hardware
Cloud
Other Categories
Warranty + Support
Average Monthly Charge per category by Synoptek (2025)
Professional Services (“People Cost”) amounts to ~$1.0M annually

## Slide 6: Well positioned to migrate Security & DevOps, additional resources required for IT
Annual cost of additional resources needed to replace Synoptek
Function | Transition Readiness | Additional annual cost of resources + licenses required for transition | Timeline of hiring resources
Security |  | $0 | N/A
DevOps |  | ~$350K | One hire by Jan 2026
Corporate IT |  | ~$650K | Two IT resources hired by Nov 2025, one hired by Jan 2026

## Slide 7: Decision: Migrate all three services away from Synoptek or just two?
Option | Pros | Considerations
(a) Migrate all three services from Synoptek: Security, Corporate IT, and DevOps | A full transition removes legacy friction, accelerates decision-making, and streamlines execution. Aligns the organization around a clear direction, with simultaneous improvement across all service areas. Establishes modern, integrated capabilities built to support expansion and innovation at scale. | Will require hiring extra resources in 2025 Resource constraints in insourcing Corporate IT and onboarding new employees, while simultaneously managing the Vegas and Boston office relocations
(b) Migrate Security and DevOps from Synoptek, sign a new one-year contract for Corporate IT with Synoptek | No extra resources required in 2025 Maybe easier to execute against | Employee support, laptop performance issues, laptop inventory issues and onboarding experience will remain unchanged

## Slide 8: Migration Timeline (assuming migration of all 3 services)
Oct
Nov
Dec
Jan
Feb
Mar
Administrative
IT
DevOps
Security
Contract Review
Hire IT Mgr
Hire IT Tech
Notify Synoptek
Training & Transition of service desk
Hire IT Tech
Microsoft/Azure account transition
Procurement transition
Infrastructure setup/backup/patching
Infrastructure alerting/monitoring
ITSM Response
KnowBe4
CrowdStrike rollout

## Slide 9: Appendix